## FrameworkDevelopment
S.No. | Assignee | Pattern | Description | Deadline
1 | Umesh | Factory | User/Customer Creation | 2016-07-10 | Y
2 | Jivan | Command | Save User/Product/Customer/Checkin/checkout | 2016-07-10
3 | Umesh | Template | checkout process / checkin process | 2016-07-10
4 | Jivan | Strategy | Email/SMS Notifier | 2016-07-10
5 | Fisseha | Bridge | Email/SMS Sender | 2016-07-11
6 | Fisseha | Singleton | DbConnectionPool | 2016-07-11
7 | Umesh | Façade | Facades for User, Product, Customer, Fine, Fee | 2016-07-11
8 | Jivan | Proxy | Protection | 2016-07-11
9 | Fisseha | Iterator | ASDSortedList for Person (Polymorphic) | 2016-07-11
10 | Jivan | Decorator | Logger - Console, File, Db | 2016-07-11

## ApplicationDevelopment
S.No. | Assignee | Tasks | Deadline | Status
1 | Umesh | CRUD UI for System User - Admin, Staff | 2016-07-12
2 | Jivan | CRUD UI for Car | 2016-07-12
3 | Fisseha | CRUD UI for Customer | 2016-07-12
4 | Jivan | UI for Checkout Process | 2016-07-12
5 | Umesh | UI for Checkin Process | 2016-07-12
6 | Fisseha | UI for Login/Logout Process | 2016-07-12
7 | All | Logging Exceptions, Warning, Info etc. | 2016-07-12